## Timeline
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | Comparing Unsupervised and Supervised Techniques for Instance-level Segmentation: Cityscapes Dataset​
[5 empty] | PHASE ONE | [34 empty] | PHASE TWO | [41 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Team Composition | All | 2022-01-17 | 2022-02-01 | 14 | bar: 2022-01-17 M to 2022-01-31 T
Introduction & Background | Andy and JD | 2022-02-02 | 2022-02-17 | 15 | bar: 2022-01-31 W to 2022-02-14 R
Problem Definition | Kartik | 2022-02-02 | 2022-02-17 | 15 | bar: 2022-01-31 W to 2022-02-14 R
Methods | Danny and Vivek | 2022-02-02 | 2022-02-17 | 15 | bar: 2022-01-31 W to 2022-02-14 R
Potential Dataset | All | 2022-02-02 | 2022-02-17 | 15 | bar: 2022-01-31 W to 2022-02-14 R
Potential Results & Discussion | Kartik | 2022-02-02 | 2022-02-17 | 15 | bar: 2022-01-31 W to 2022-02-14 R
Video Creation & Recording | All | 2022-02-17 | 2022-02-24 | 7 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-14 F to 2022-02-21 W
GitHub Page | Danny | 2022-02-17 | 2022-02-24 | 7 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-14 F to 2022-02-21 W
Project Proposal | All | 2022-02-17 | 2022-02-24 | 7 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-14 F to 2022-02-21 W
Model 1(M1): Unsupervised Domain Adaptation
M1 Data Input Pipeline | Andy and JD | 2022-02-24 | 2022-03-04 | 10 | bar: 2022-02-21 M to 2022-02-21 W; 2022-02-21 F to 2022-02-28 F
M1 Modify and clean SOTA code | Danny | 2022-02-24 | 2022-03-04 | 10 | bar: 2022-02-21 M to 2022-02-21 W; 2022-02-21 F to 2022-02-28 F
M1 Training and validation | Danny | 2022-03-03 | 2022-03-10 | 7 | bar: 2022-02-21 M to 2022-02-21 W; 2022-02-21 F to 2022-02-28 F
M1 Hyper parameter tuning | Danny | 2022-03-03 | 2022-03-10 | 7 | bar: 2022-02-21 M to 2022-02-21 W; 2022-02-21 F to 2022-02-21 U; 2022-02-28 R to 2022-03-07 R
M1 Results Evaluation | Danny | 2022-03-10 | 2022-03-24 | 14 | bar: 2022-03-07 F to 2022-03-21 F
M1 Qualitative analysis | All | 2022-03-25 | 2022-03-30 | 5 | bar: 2022-03-21 S to 2022-03-28 W
Model 2(M2): Model Chaining
M2 Data Input Pipeline | Andy and JD | 2022-02-24 | 2022-03-04 | 10 | bar: 2022-02-21 F to 2022-02-28 F
M2 Modify DETR | Andy and JD | 2022-02-24 | 2022-03-10 | 16 | bar: 2022-02-21 F to 2022-02-28 F
M2 Modify MySegO | Andy and JD | 2022-03-03 | 2022-03-10 | 7 | bar: 2022-02-21 F to 2022-02-28 F
M2 Combine both methods | Andy and JD | 2022-03-03 | 2022-03-10 | 7 | bar: 2022-02-21 F to 2022-02-21 U; 2022-02-28 R to 2022-03-07 R
M2 Hyperparameter tuning and testing | Andy and JD | 2022-03-10 | 2022-03-24 | 14 | bar: 2022-03-07 F to 2022-03-21 F
M2 Results Evaluation and analysis | All | 2022-03-25 | 2022-03-30 | 5 | bar: 2022-03-21 S to 2022-03-28 W
Model 3(M3): Density Based Clustering
M3 Data Input Pipeline | Andy and JD | 2022-03-11 | 2022-03-20 | 9 | bar: 2022-03-07 F to 2022-03-14 U
M3 Image data Transformation | Kartik | 2022-03-11 | 2022-03-20 | 9 | bar: 2022-03-07 F to 2022-03-14 U
M3 Implementation & Coding | Kartik | 2022-03-19 | 2022-03-27 | 8 | bar: 2022-03-14 S to 2022-03-21 U
M3 Hyperparameter tuning | Kartik | 2022-03-19 | 2022-03-27 | 8 | bar: 2022-03-14 S to 2022-03-21 U
M3 Results Evaluation | All | 2022-03-27 | 2022-04-11 | 14 | bar: 2022-03-28 T to 2022-03-28 U; 2022-04-04 T to 2022-04-11 R
M3 Cluster Visualization | Kartik | 2022-04-11 | 2022-04-16 | 5 | bar: 2022-04-11 M to 2022-04-11 S
Midterm Report | All | 2022-03-28 | 2022-04-05 | 7 | bar: 2022-03-28 M to 2022-03-28 U; 2022-04-04 T to 2022-04-04 W
Model 4 (M4): Supervised Fine-tuning
M4: Model Design | All | 2022-03-11 | 2022-03-20 | 9 | bar: 2022-03-07 F to 2022-03-14 U
M4 Data Input Pipeline | Vivek | 2022-03-11 | 2022-03-20 | 9 | bar: 2022-03-07 F to 2022-03-14 U
M4 Pretrained COCO, test on Cityscape | Vivek | 2022-03-19 | 2022-03-27 | 8 | bar: 2022-03-14 S to 2022-03-21 U
M4 Train and test Cityscape | Vivek | 2022-03-19 | 2022-03-27 | 8 | bar: 2022-03-14 S to 2022-03-21 U
M4 Code modification for transfer learning | Vivek | 2022-03-27 | 2022-04-11 | 14 | bar: 2022-03-28 T to 2022-03-28 U; 2022-04-04 T to 2022-04-11 R
M4 Results Evaluation and analysis | All | 2022-04-11 | 2022-04-16 | 5 | bar: 2022-04-11 M to 2022-04-11 S
M4 Pairwise comparison of train/test combinations | All | 2022-04-11 | 2022-04-16 | 5 | bar: 2022-04-11 M to 2022-04-11 S
M1-M4 Qualitative Comparison | All | 2022-04-01 | 2022-04-22 | 21 | bar: 2022-03-28 F to 2022-03-28 U; 2022-04-04 T to 2022-04-18 F
Video Creation & Recording | All | 2022-04-15 | 2022-04-26 | 11 | bar: 2022-04-11 F to 2022-04-25 M
Final Report Writing | All | 2022-04-18 | 2022-04-26 | 8 | bar: 2022-04-18 M to 2022-04-25 M

## Overview
GANTT CHART |  |  |  |  | https://goo.gl/PXLbMe
PROJECT TITLE | TITLE
|  | PHASE ONE |  | PHASE TWO |  |  |  |  | PHASE THREE
TASK TITLE | TASK OWNER | 2022-01-17 | 2022-02-24 | 2022-02-24 |  | ... |  | 2022-04-05 | 2022-04-05 | ... | 2022-04-26
Project Proposal
Introduction & Background | Karishma
Problem Definition | Tim
Methods | Bryan
Potential Results & Discussion | Noah & Gabby
Video Recording | All
GitHub Page | Karishma
Unsupervised Domain Adaptation
Data Sourcing and Cleaning | Tim
Model Selection | Karishma
Data Pre-Processing | Tim
Model Coding | Karishma
Results Evaluation and Analysis | Tim
Midterm Report | All
Model Chaining
Data Sourcing and Cleaning | Gabby
Model Selection | Noah
Data Pre-Processing | Gabby
Model Coding | Noah
Results Evaluation and Analysis | Gabby
Density Based Clustering
Supervised Fine-tuning
Data Sourcing and Cleaning | Bryan
Model Selection | Bryan
Data Pre-Processing | Bryan
Model Coding | Bryan
Results Evaluation and Analysis | Bryan
Model comparison and Report Writing
Model Comparison | Tim
Presentation | All
Recording | All
Final Report | All
sn